## Cover
QA Report
Phase | : | 1
Release | : | WK-2
Project | : | Driver
Build | : | 1.0.0
Date | : | 29.09.23
Reporter | : | Rushmia Ahmed

## Functionality Verification
E-ComeTrue WK-11 Release Checklist
# | Module | Features | Verified by SE | TL Confirmation | Verified By QA | Status (by QA) | SE/TL Comment | QA Comment
1 | Add Record | 1. ARF | No | No | No | NG |  | #479758 ##479551 #479543
| Dashboard | Blackspot | No | No | No | NG |  | #479833
| Record List | Edit | No | No | No | NG |  | #479525
| Manage Duplicate Records |  | No | No | No | NG |  | #479835
2 | Map | 1. Pop up view 2.Save Filter | No | No | No | NG |  | #479568 #479559 #479583
[N.B: We have checked all screens and found some major and minor issues, these are posted in Redmine]

## Release Summary
E-ComeTrue WK-11 Release Summary Report
Release Info |  | Browser & Device List
Release Name | WK-2 | Serial# | Tested Device Name & Model(Windows) | OS Version
Version Name | V-1.0.0 | 1 | PC (Windows) | Win-10
Release Topic | 1. Login 2. Dashboard 3.My Account 4.Map 5.Add Record 6.Record List 7.Manage Duplicate Records
Released By | Rushmia Ahmed | # | Web Browser | Version
Verified By | Abdul Qadir | 1 | Windows - Chrome | Version 116.0.5845.188
Non Executed Test Type:
1 | Functional,UI
Non Executed Test Type:
1 | Regression
2 | Security
3 | Virus Checking
4 | Reliability
5 | Usability
6 | Performance
7 | Device compatibility

## Graphical Report
Test Case Execution Report (WK-11)
| Build Version No: | 1.0.0
| Total WK-02-Test cases: | 121
| Test Environments (Browsers): | 1
| Total Executable test cases: | 121
| Test Cases Executed: | 118
| Un-Executed: | 0
| Passed: | 109
| Failed: | 9
| WIP: | 0
| NA: | 4
| Blocked: | 0
| Total Reported Bugs : | 9
| Open | 9
| Done but not assigned to QA team: | 0
| Verified | 0
| Rejected | 0
| In Progress | 0
| Not A Bug | 0
| Assigned | 0
| Reopened | 0
| Reviewed | 0
| Duplicate | 0
| Closed | 0
| Reported Bugs : (All Weeks) | 9
| Open | 9
| Done | 0
| Verified | 0
| Deferred | 0
| In Progress | 0
| Not A Bug | 0
| Closed | 0
| Reopened | 0
| Reviewed | 0
| Duplicate | 0
| Rejected | 0
| Open | 0
| Assigned | 0
| Immediate : | 0
| Urgent : | 0
| High: | 2
| Normal: | 2
| Low: | 5
| Total: | 9
Test Execution summary
WK-11-Bug summary
Phase-1 Full - Bug summary
Total Bugs (Priority wise):

## WK_02_Bug_list
DRIVER (WK-2)
| Bug Type | Quantity
| UI: | 3
| Functional: | 6
| Total: | 9
| # | Bug ID | Bug Summary | Status | Priority
| 1 | https://redmine.bjitgroup.com/redmine/issues/479758 | [V-1.40] [Add Record ]After removing the image from the incident images field, the image file name is still shown next to the "Choose Files" button. | Open | High
| 2 | https://redmine.bjitgroup.com/redmine/issues/479568 | [V-1.40] [Map]The loss amount for "Motor Collision" (মোটর) is not entirety displayed in the detail view of the overall economic loss and societal harm amount in terms of BDT; the bottom part of the amount is suppressed. | Open | High
| 3 | https://redmine.bjitgroup.com/redmine/issues/479833 | [V-1.40] [Dashboard] Blackspots by Severity" section does not display any blackspots as indicated in the user manual on the Dashboard | Open | Urgent
| # | Bug ID | Bug Summary | Status | Priority
| 1 | https://redmine.bjitgroup.com/redmine/issues/479525 | [V-1.40] [Record List] Despite having images corresponding with the record in the "Incident Files" and "Location Sketch" fields, the "Choose Files" button in the "Edit a Record" view displays as "No file chosen" | Open | Normal
| 2 | https://redmine.bjitgroup.com/redmine/issues/479551 | [V-1.40] [Add Record] After successfully deleting an image from using the 'x' icon, the "Incident Images" and "Location Sketch" both fields does not allow re-uploading the same image again | Open | High
| 3 | https://redmine.bjitgroup.com/redmine/issues/479559 | [V-1.40] [Map] The age filter accepts floating-point numbers as input | Open | Urgent
| 4 | https://redmine.bjitgroup.com/redmine/issues/479543 | [V-1.40] [Add Record] Multiple images cannot be uploaded consecutively in the incident images field. | Open | Urgent
| 5 | https://redmine.bjitgroup.com/redmine/issues/479583 | [V-1.40] [Map] The "Occurred Date" filter permits the selection of future dates and allows saving the filter with these future dates | Open | Immediate
| 6 | https://redmine.bjitgroup.com/redmine/issues/479835 | [V-1.40] [Manage Duplicate Records] "Potential Duplicate Records" page does not display any duplicate records despite the existence of duplicate records based on location, date, and time criteria | Open | Normal
WK-11 - Bug summary
UI Bugs:
Functional Bugs:

## Bug_trend
Release | Test case | Bugs | Resolved | Trend
WK-02 | 121 | 9 | 2 | 0

## Defect density
Release | Effort | Defect | Defect density | Trend
WK-02 | 121 | 9 | 0.07438 | 0.375